## 工作表1
Phase | Step | Description | Responsible Auditor | Planned Start | Planned End | Status | Notes
Planning | Define Scope | Identify objectives | scope | and criteria | Audit Manager | 2025-11-01 | 2025-11-02 | Not Started
Planning | Risk Assessment | Assess risks and prioritize areas | Audit Manager | 2025-11-03 | 2025-11-04 | Not Started
Planning | Engagement Letter | Send notification to auditee | Audit Manager | 2025-11-05 | 2025-11-05 | Not Started
Planning | Entrance Meeting | Discuss scope | timeline | expectations | Audit Manager | 2025-11-06 | 2025-11-06 | Not Started
Fieldwork | Control Testing | Test design and operating effectiveness | Auditor A | 2025-11-07 | 2025-11-12 | Not Started
Fieldwork | Transaction Testing | Sample and test transactions | Auditor B | 2025-11-13 | 2025-11-15 | Not Started
Fieldwork | Interviews | Interview key personnel | Auditor C | 2025-11-16 | 2025-11-17 | Not Started
Documentation | Workpapers | Document evidence and results | Auditor A | 2025-11-18 | 2025-11-20 | Not Started
Documentation | Review | Supervisor reviews workpapers | Audit Manager | 2025-11-21 | 2025-11-22 | Not Started
Reporting | Draft Report | Prepare draft with findings | Audit Manager | 2025-11-23 | 2025-11-25 | Not Started
Reporting | Exit Meeting | Discuss findings with auditee | Audit Manager | 2025-11-26 | 2025-11-26 | Not Started
Reporting | Final Report | Issue final report to stakeholders | Audit Director | 2025-11-27 | 2025-11-28 | Not Started
Reporting | Follow-up | Track remediation of findings | Audit Manager | 2025-12-01 | 2025-12-15 | Not Started